## Summary-of-Submittals
REQUIRED DELIVERABLES | PROJECT PHASES | [5 empty] | ISSUER | RECIPIENT-REVIEWER | STANDARD REFERENCE |  | INPUTS FROM THE CITY OF GREATER SUDBURY
| PRELIMINARY DESIGN | DETAILED DESIGN | CONSTRUCTION AND PROGRAMMING | FAT | SAT & COMMISSIONING | POST-COMMISSIONINNG (AS-BUILT) |  |  | DOCUMENT | SECTION NUMBER
Standards Deviation Request Form (* as required, it is not a mandatory submittal) | √* | √* | √* | √* | √* | √* | Consultant/Contractor/System Integrator | City of Greater Sudbury | A - General Requirements | 5.3.1 | - Current version of City of Greater Sudbury SCADA, Controls & Instrumentation Systems Design Standards, and City of Greater Sudbury standard software (PAC and HMI) routines - Assignment of City of Greater Sudbury's SCADA Standards Leader for the project, and their contact information - Approvals on deviation/revision forms as required
Standards Revision Request Form (* as required, it is not a mandatory submittal) | √* | √* | √* | √* | √* | √* | Consultant/Contractor/System Integrator | City of Greater Sudbury |  | 7
Standards Software Revision Request Form (* as required, it is not a mandatory submittal) |  |  | √* | √* | √* | √* | Contractor/System Integrator | City of Greater Sudbury |  | 7
Section B Deliverables - Pre-design (for specific items involved, refer to Section C, D, E, F, G as applicable to pre-design) | √ | [5 empty] | Consultant | City of Greater Sudbury | B - Automation Systems Project Delivery | 2.1 | - Existing As-built documentation as available and as applicable to the scope - Master P&IDs and master PCN's, as available and as applicable to the scope - Control Systems Integrator evaluation and selection - Access to facility (coordinated by Consultant/Contractor) - Operations support (for site work, input during preliminary and detailed design, testing and commissioning) - Submittals' review and witnessed testing - Licenses for software to be installed on site - On-site training facilities - Operation and Maintenance manual sample
Section B Deliverables - Detailed Design (for specific items involved, refer to Section C, D, E, F, G as applicable to detailed design) |  | √ |  |  |  | √ | Consultant | City of Greater Sudbury |  | 3.1
Field Verification Report | √ | [5 empty] | Consultant | City of Greater Sudbury |  | 2.1
Construction Cost Estimates | √ | √ |  |  |  |  | Consultant | City of Greater Sudbury |  | 2, 3
Vendor/Equipment Pre-selection Specifications and Tender Package |  | √ |  |  |  |  | Consultant | City of Greater Sudbury |  | 5
Shop Drawings - Instrumentation |  |  | √ |  |  | √ | Contractor | Consultant, City of Greater Sudbury |  | 6.2
Shop Drawings - PAC Panels (ICPs), Layout and Bill of Material, Wiring |  |  | √ |  |  | √ | Contractor | Consultant, City of Greater Sudbury |  | 6.2
Vendor Package Integration / Interface Plan |  |  | √ |  | √ | √ | Contractor | Consultant, City of Greater Sudbury |  | 5
Vendor Package Data Exchange |  |  | √ |  | √ | √ | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 5
Instrument Control Panel FAT Test Plan |  |  | √ |  |  |  | Contractor | Consultant, City of Greater Sudbury |  | 6.3.1
Completed Panel FAT Test Form and Comments Sheets |  |  |  | √ |  |  | Contractor | Consultant, City of Greater Sudbury |  | 6.3.1
PAC&HMI Software Submittal |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 6.3.2
Software FAT Test Plan and Checklist |  |  | √ |  |  |  | System Integrator | Consultant, City of Greater Sudbury |  | 6.3.2
Completed Software FAT Test Forms and Comments Sheets |  |  |  | √ |  |  | System Integrator | Consultant, City of Greater Sudbury |  | 6.3.2
ICP Installation Checklist |  |  |  |  | √ |  | Contractor | Consultant, City of Greater Sudbury |  | 7.1
Instrument Installation and Verification Checklist |  |  |  |  | √ |  | Contractor | Consultant, City of Greater Sudbury |  | 6.4, 7.2
SAT Signal Testing Check Sheet |  |  |  |  | √ |  | Contractor | Consultant, City of Greater Sudbury |  | 7.3, 7.4
Completed Hardware SAT Test Report and Signoff |  |  |  |  | √ |  | Contractor | Consultant, City of Greater Sudbury |  | 7.1-7.3
Implementation/Commissioning Plan |  |  | √ |  | √ |  | Contractor | Consultant, City of Greater Sudbury |  | 8
Software SAT Test Plan |  |  | √ |  |  |  | System Integrator | Consultant, City of Greater Sudbury |  | 7.4
Completed Software SAT Test Report and Signoff |  |  |  |  | √ |  | System Integrator | Consultant, City of Greater Sudbury |  | 7.4
SCADA, Controls and Instrumentation System Consultant's Training Plan and Training Manual |  |  |  |  | √ |  | Consultant | City of Greater Sudbury |  | 9.1
SCADA, Controls and Instrumentation System Contractor's Training Plan (Hardware, Software) |  |  |  |  | √ |  | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 9.2
Contractor's Training Documents (handouts, slides, manuals, etc.) |  |  |  |  | √ |  | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 9.2
SCADA, Controls and Instrumentation System Operation and SCADA, Controls and Instrumentation System Maintenance Manual; List of Warranties with Start Dates and Durations |  |  |  |  | √ | √ | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 10
SCADA, Controls and Instrumentation System Inventory and Spare Parts Inventory |  |  | √ |  |  | √ | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 11
Section B Consultant's Design Deliverables - as-built red-lines and updates |  |  |  |  | √ | √ | Contractor/System Integrator | Consultant, City of Greater Sudbury |  | 13
Section B Consultant's Design Deliverables - As built | [5 empty] | √ | Consultant | City of Greater Sudbury |  | 13
Devices' (process equipment and instrumentation, SCADA system/network equipment), and Panels' Tag Lists | √ | √ |  |  |  | √ | Consultant | City of Greater Sudbury | C - Equipment and Data Tagging (Submittals listed in this Section are integral part of the overall project delivery submittals described and indicated in Section B) | 1.2 | - Assignment of any new codes to be used in standard tagging - City of Greater Sudbury equipment forms for existing equipment modified/deleted under the scope (as applicable) - Review / approval of tag lists, update of City's master lists
Equipment Add/Delete Forms |  | √ | √ |  |  | √ | Consultant/Contractor | City of Greater Sudbury |  | 1.2
Shop Drawings - Physical Tagging List and Samples |  |  | √ |  |  |  | Contractor | Consultant, City of Greater Sudbury |  | 3
PAC Tag List (Database) |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 2.2.5
SCADA Tag List (Database) |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 2.2.5
P&ID's | √ | √ |  |  | √ | √ | Consultant/Contractor | City of Greater Sudbury | D - Instrumentation & Control Systems Design (Submittals listed in this Section are integral part of the overall project delivery submittals described and indicated in Section B) | 2 | - Existing facility PCN and drawings (as applicable) or sample control narrative - CAD Standards - Relevant network and SCADA system infrastructure/configuration information
PAC Panel Layout Drawings and Bill of Material, Schedule of ICP's |  | √ |  |  |  | √ | Consultant | City of Greater Sudbury |  | 6
PAC Panel Schematics, and power circuits and I/O loop Wiring |  | √ |  |  |  | √ | Consultant | City of Greater Sudbury |  | 6
Device and Instrument List, Instrument Data Sheets |  | √ |  |  |  | √ | Consultant | City of Greater Sudbury |  | 5.2
Process Control Narrative - PCN with Lists of Setpoints, Alarms, Calculated Parameters, Historical Logging, and Trending and Reporting Requirements (* Process Narrative) | √* | √ | √ | √ | √ | √ | Consultant/Systems Integrator | City of Greater Sudbury |  | 3
Technical Specifications (instrumentation and control hardware and wiring, network, software, testing and documentation requirements, including templates for Contractor's and System Integrator's submittals as part of Section B) - Division 13, Division 17, coordination with Divisions 1, 11, 15, 16 |  | √ | √ |  |  | √ | Consultant/Contractor (shop drawings during construction) | City of Greater Sudbury |  | 5, 6
Controller Hardware Bill of Materials (all PACs) |  | √ | √ | √ | √ | √ | Consultant/ Contractor | City of Greater Sudbury/Consultant, City of Greater Sudbury | E - Controller Standards (Submittals listed in this Section are integral part of the overall project delivery submittals described and indicated in Section B) | 2.1 | - Relevant info related to current software versions, software purchasing and licensing, firmware versions - Standard PAC Routines - Existing PAC programming affected by the scope, as applicable - Review and approval of hardware and software submittals
Controller Hardware layout (rack layout) for each PAC |  | √ | √ | √ | √ | √ | Consultant/ Contractor | City of Greater Sudbury/Consultant, City of Greater Sudbury |  | 2.1
Controller Communication Interfaces and Remote I/O, as applicable |  | √ | √ | √ | √ | √ | Consultant/ Contractor | City of Greater Sudbury/Consultant, City of Greater Sudbury |  | 2.1
Controller application software project file for each PAC being programmed |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 2.2
Configuration report indicating all configuration parameters for each PAC, including processor, I/O modules, communication cards, etc. |  |  |  |  | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 2.2
OIT application sofrware for each OIT being programmed |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 3
Network Architecture Drawing and Network Layout Drawing | √ | √ |  |  |  | √ | Consultant/ Contractor | City of Greater Sudbury/Consultant, City of Greater Sudbury | F - Networks and Communications (Submittals listed in this Section are integral part of the overall project delivery submittals described and indicated in Section B) | 3.8 | - Free issue of hardware (workstations, network switches) and associated software licenses (O/S etc.) - Range of IP addresses to be used in the project
NetworkWiring and Terminations Diagrams (Fibre/Copper) |  | √ | √ |  |  | √ | Contractor | Consultant, City of Greater Sudbury |  | 3.8
Network Cabling Conduit Layout Drawing |  |  | √ |  |  | √ | Consultant/ Contractor | Consultant, City of Greater Sudbury |  | 3.8
Network Equipment Tagging |  | √ | √ |  |  | √ | Consultant/ Contractor | City of Greater Sudbury/Consultant, City of Greater Sudbury |  | 3.8
Shop Drawings - Network Components, Labelling and Cabling, catalog sheets. |  |  | √ |  |  | √ | Contractor | Consultant, City of Greater Sudbury |  | 3.8
Network Test Reports and Operation and Maintenance Manual |  |  | √ |  | √ | √ | Contractor | Consultant, City of Greater Sudbury |  | 3.8
SCADA Computer hardware specification, schedule of computers with tagging |  | √ | √ |  |  | √ | Consultant/Contractor | Consultant, City of Greater Sudbury | G - SCADA Standards (Submittals listed in this Section are integral part of the overall project delivery submittals described and indicated in Section B) | 2.2 | - Standard SCADA Software Routines and affected Existing Programs
SCADA application software (graphic files, including pop-ups, database import file, all relevant driver and configuration files), and screen shots |  |  | √ | √ | √ | √ | System Integrator | Consultant, City of Greater Sudbury |  | 2.3
List of tags for historical data collection, list of reports |  | √ | √ |  |  | √ | Consultant, System Integrator | Consultant, City of Greater Sudbury |  | 3.4
SCADA Training Manual, SCADA, Controls and Instrumentation System Manual |  |  |  |  | √ |  | System Integrator | Consultant, City of Greater Sudbury |  | 2.4