## Slide 1: Equipment / System
START
Received Submittal
for Equipment
Approval
Equipment
Manufactured
at Shop
Approval of
Factory
Acceptance test
Yes
No
Fail
Pass
Contractor to
submit Manufacturer’s
Certificate of
Proper Installation
Pre-Start
Inspection
Follow
START UP
FLOWCHART
Delivered to Site
and
Installed
Submit Manufacturer’s
Certificate of
Compliance
A
Appendix B-9 Commissioning Flow Charts
City of Greater Sudbury SCADA, Controls & Instrumentation Systems Design Standards
Software Development and Pre-Factory Acceptance (pre-FAT) Submittal
Loop Checks and Software Pre-Site Acceptance Testing (Pre-SAT), Pre-SAT Submittal and Approval process
Software SAT
Software Post -SAT submittal
Similarly , Software Pre-FAT Submittal, Approval process, Software Factory Acceptance Test (FAT), Post FAT submittal
Software FAT and Approval of FAT
Software Pre-FAT Submittal Approval process
Post-FAT Submittal
Software
Version 1.0 April, 2018
Water & Wastewater Services

## Slide 2: Start up & Commissioning
FINISH
Pass
Training
Period
(see Page 3)
COMMISSIONING SCHEDULE to identify time lines for each item and account for Notice to Commence requirements in specifications
Water
Water
Start-Up Test
Performance Testing
(Commissioning)
15 Days
Operational Testing
(Commissioning)
5 Days
Pass
Pass
Fail
Location/Project
Fail
OPERATIONAL RESPONSIBILITY
Contractor
City of Greater Sudbury
Complete
Deficiencies
A
Cert of Proper Install.
Pre-Start H&S
Inspection
Cert of Proper Install.
Inspection
Start From Equipment Flowchart
Pre-Start H&S
Deficiencies
Fail
Water
Fail
Programming
5-day Water Test
Pass
Fail
Pass
Pass
Pass
Closed Loop Water
Obtain all regulatory approvals
Manuals
(see Page 4)
Substantial Performance
Total Performance of Work
Appendix B-9 Commissioning Flow Charts
City of Greater Sudbury SCADA, Controls & Instrumentation Systems Design Standards
Version 1.0 April, 2018
Water & Wastewater Services

## Slide 3: Training
START
Submittal
Draft
Training Program
Approval
FINISH
Yes
No
Operation
and
Routine Maintenance
Training
Non-
Routine Maintenance
Training
In Class
Operation
On Site
Maintenance Staff
Operation Staff
Electrical & Instrumentation
Personnel
City of Greater Sudbury to
Provide the List of Personnel
Maintenance
Shop Drawing Phase
Final Training Program
Submit Training Material
CD’s & DVD’s
40 Days Before
Start-up
Final Inspection and
Start-Up
Functional Test
Schedule of
Training
30 Days before Start -up
Yes
No
2 Per Shift
Each Sessions
No
Monday to Friday 7am to 3pm
Monday to Friday 7am to 3pm
Successfully
Completed
Training
Yes
Tuesday & Wednesday Preferred
Appendix B-9 Commissioning Flow Charts
City of Greater Sudbury SCADA, Controls & Instrumentation Systems Design Standards
Operation
Maintenance
Process Training
(By Consultant)
&
Training SCADA
(By Contractor)
Version 1.0 April, 2018
Water & Wastewater Services

## Slide 4: Manuals
START
Submittal
Draft
Table of Contents
Approval
YES
No
45 days after Shop Drawing approval
Go to
Start-Up Testing
(see Page 2)
Submittal
Draft Manuals
Approval
No
YES
Submittal
Final Manual
All Manuals - 21 Days after approval of table of contents
Equipment O&M Manual and Add Equipment Forms - 80 Days before Start-Up and Commissioning
Appendix B-9 Commissioning Flow Charts
City of Greater Sudbury SCADA, Controls & Instrumentation Systems Design Standards
Version 1.0 April, 2018
Water & Wastewater Services