## As-built Checklist
AS-BUILT CHECKLIST | COMPLETED | N/A | REMARKS | LINKS
GENERAL TASK
- obtain the latest c-plan (including addendum & change orders to your c-drive |  |  |  | S:\draftpub\C-PLANS
- script the layers from construction to as-builts |  |  |  | S:\draftpub\AutoCAD Drafting Resources\AutoCAD Support Files\Scripts
- rename the file to city standard filing convention ex. frood8-13_c3d_CSRS_z81.dwg
- Add the most up to date as-built title block (incl property disclaimer) and update the new attributes (fields) |  |  |  | ..\AutoCAD Support Files\Title Blocks
- copy as-built survey into your file (make sure both files are in CSRS Zone81) |  |  |  | S:\draftpub\Eds-dat\PRELIMINARY
- change construction layer to existing layer to all new structures & pipes
- obtain the redline dwgs and update changes for example tops, inverts, move pipes, etc.. |  |  |  | S:\draftpub\Eds-dat\Red Line Drawings
- if available use field notes (from GIS or CITYMaps), to update inv & top of structures |  |  |  | https://sudbury.maps.arcgis.com/apps/opsdashboard/index.html#/17972b8be1074e9e9e54f70f303aa529
- if new structures, allocate a new legacy number from the legend in the key plans |  |  |  | S:\draftpub\KEY
- remove all construction notes
- check if new utilities have been added from the Municipal Consent File |  |  |  | S:\draftpub\Municipal Consents
- check the Engineering Street Files in: \\greatersudbury.ca\files\S_Eng_Street_Files |  |  |  | S_Eng_Street_Files
- show all prelim details (driveway,retaining walls, culverts, etc..) within the ROW. As per example dwg.
- update the dates on the year of construction note only if the sanitary & storm sewer or watermain as been fully replaced
- add centerline curve data if needed
2D AS-BUILT
These procedure (task) are not necessarily in this order
PLAN
- move proposed structures to new survey as per redline dwgs or survey data
- adjust the station & offset from the alignment for each structures
- replace proposed structures with existing blocks (in some cases)
- adjust pipes to new structure location
- update length, inverts, size of pipes (if nessasary)
- update service box location from the building
- update revision block as needed
PROFILE
- move structures to new station and manually adjust pipe to new inverts and tops
- revise inverts & tops in the structure label
- change the new top of asphalt from const cl profile to the existing layer
- calculate the revised grade for each pipe
- add top of watermain at each 15m interval from redlines (if available)
- remove all construction vertical curves and grade notes (labels)
- remove existing road profile and replace with proposed cl road profile.If a cross-sectional survey of the roadway is provided, generate new profile.
- remove granular 'B' baseline below road profile
- change length, size, type, grade & class (if applicable) for each pipe
C3D AS-BUILT
These procedure (task) are not necessarily in this order
PLAN
- relocate ( using grips) proposed structures to new location according to redlines or survey.
- merge pipe networks to existing. So, you should have only 3 existing pipe networks (SAN, STM & WM)
- remove duplicate structures and pipes if needed
- connect pipes to structure (using grips)
- update structure names if not already done
- update structure inverts with structure properties. Get new inverts from redlines or field notes.
- change structure style to existing style and change layer
- change structure label style to existing structure label style for each structures
- update service box location from the building
- once the redline are done, change centerline of construction alignment reference, from construction reference to CL of ROW
PROFILE
- change proposed road profile to existing style
- draw parts in profile if needed
- change propose pipes & structure layers to existing layers
- change structure label to existing label style
- add top of watermain elevation at each 15m interval from redlines
- remove all construction vertical curves, grades labels and final top of asphalt elevation
FINALIZING DRAWING CHECKS
Spell check
Purge/audit
Remove all xref
Promote data shortcuts
Zoom extents on all tabs
Lock viewports
Make layer 0 current
In model space set UCS to World
Change date in title block when done
Update filename to standards
Remove all survey layers (ex. X_tree) and construction layers
Do a peer review within draftsperson. Drawing should look like the example street |  |  |  | S:\draftpub\AutoCAD Drafting Resources\Example Drawings
Archive to Drafting Clerk once complete