Seasonal Shutdown

This Special Provision shall apply to: * [Designer to specify] (e.g. Entire Roadway within contract limits, or STA x to STA x, Street x to Street x).

Prior to the Contractor suspending Work for seasonal shutdown, or by December 24 **[Designer to specify] , whichever is earlier, the following Work shall be completed on the above roadways on which construction operations have commenced and which are to remain open to public traffic:

*** [Designer to specify/add to the following as required.]

- The roadbed shall be completed to the specified grade and cross section of the granular base;

- The roadbed shall be paved with all binder courses of asphalt, including structure adjustments to the corresponding elevation of the top of asphalt;

- Temporary pavement markings shall be applied as specified elsewhere;

- Shoulders shall be completed to the corresponding elevation of the top of asphalt.

When, in order to comply with requirements above, the Contractor does not comply with applicable restrictions, the Contractor shall be responsible for all costs and Work associated with the removal and replacement of the deficient materials, including the provision of any required temporary measures and traffic control where removal and replacement are deemed necessary by the Contract Administrator.

When the Contractor has performed Work which did not comply with the applicable restrictions:

- The Contractor shall be responsible for the costs incurred by the Owner in maintaining the roadway in a condition satisfactory for the travelling public during seasonal shutdown, excluding the costs of applying de-icing salts, abrasives and snow-plowing operations; and

- Payment at the contract prices for the Work will be withheld until any necessary removal and replacement of the roadway as deemed necessary by the Contract Administrator has been completed following the seasonal shutdown.