## Slide 1: PAYMENT UPDATES
Project Controls Coordinators:
Dave Barrett : dave.barrett@greatersudbury.ca
Vanessa Chiesa-Javor : vanessa.chiesa-javor@greatersudbury.ca
project.controls@greatersudbury.ca

## Slide 2: Ontario Construction Act Mandatory Annual Holdback (Bill 216)
Annual Release of Holdback
Effective January 1, 2026, Owners must release holdback each year on the contract anniversary date for projects over 12 months.

## Slide 3: Mandatory Annual Holdback
Publication of Notice (Documentation Requirement)
Owners must publish a Notice of Annual Release of Holdback (Form 6) within 14 days after each anniversary.
Notice must state the holdback amount and intended payment date.
Notices must be published on Daily Commercial News, Link2Build, or Ontario Construction News.

## Slide 4: Mandatory Annual Holdback
Release Timelines
Owners must release holdback between 60 and 74 days after publishing the notice (unless a lien is preserved).
Transition Provisions
A. Contracts after Jan 1, 2026: Annual holdback applies immediately.
B. Contracts between July 1, 2018 and Jan 1, 2026: Applies on second anniversary after Jan 1, 2026.

## Slide 5: Proper Invoice Submissions
Signed Copy of Proper Invoice
Documentation
  Updated Construction Schedule
  CCDC 9A-18 Statutory Declaration
  Current WSIB Clearance Certificate
  Current Insurance Certificate

## Slide 6: Substantial Completion & Contract Completion
Application found on the website
  https://www.greatersudbury.ca/do-business/infrastructure-and-city-construction/engineering-services/procurement-and-contract-forms/substantial-completion-formr1-pdf/
Email application to:
  Project Manager
  Project Controls Coordinators
Review of Application based on the 3-2-1 Calculations as outlined in the Construction Act
Application has been approved: Project Controls will commence paperwork
Application not approved: Project Manager will notify Contractor
Email Proof of Publication to Project Controls