17. Payment Adjustment for Changes in The Fuel Price Index

Scope

The purpose of this specification is to provide price adjustments between parties based on fluctuations in fuel prices over the term of the contract.

Reference Standards, Specifications and Publications

This section identifies additional standards, specifications and publications that are referenced in the development or are considered part of this document.

- Ontario Ministry of Transportation

Fuel Cost Adjustment Index – on their web page at the following link: https://www.raqs.merx.com/public/bulletin/bulletin.jsf

Basis of Payment

Agreement Between Parties

It is agreed by the parties to the contract that it is impracticable and difficult to ascertain actual fuel consumed on the contract, and that the parties hereto agree that for the purpose of calculating the total fuel price adjustments, that the process outlined in this specification will be used.

Fuel Cost Adjustment Index

The City will adjust the payment to the Contractor based on changes to the MTO's Fuel Cost Adjustment (FCA). The Ontario Ministry of Energy, Northern Development and Mines will calculate the FCA based on the average diesel rack fuel price including taxes for the month published. The FCA is published at the end of each month on the MTO web site at the link:

https://www.raqs.merx.com/public/bulletin/bulletin.jsf

This web site lists the average fuel price for the current calendar month the FCA is published along with all preceding months for the current and preceding calendar year.

The Contractor is responsible for any flow through to truckers, subcontractors, shippers, and suppliers as required. The City will not provide any additional compensation for this purpose other than provided through this special provision.

Payment Adjustment

A payment adjustment, excluding any payments for Changes in the Work and Additional Work, will be calculated monthly and applied to the monthly progress payment. Payment will be included on the next progress payment.

The current progress payment will use the most recent published FCA.

Payment or credit are subject to taxes and holdback.

A payment adjustment for work done after the approved time for completion of the Contract has expired, including the expiration of any extensions of time that have been granted, shall be the lesser of the fuel index in the last month of the Contract or the month in which the work was completed.

Fuel Price Adjustment Calculation

a) 	The Contractor’s payment adjustment for each month shall be calculated using the following formula:

Cfpa=Ctem × (I-Bc)100

Where:

Cfpa = fuel price adjustment paid to Contractor or Owner, in dollars

Ctem = total estimated monthly fuel consumption

I = progress payment month fuel price index (for the month that the work was completed in)

Bc = fuel price index in the month prior to the Contract tender closing

b) 	The total estimated monthly fuel consumption shall be calculated by multiplying the consumption rates in Table 8.02.04.02-1 by the work accomplished in the current month for each applicable item and totaling the volume in litres.

c) 	Only tender item quantities or work done at the tender item price shall be included in the calculation.

d) 	When (I-Bc) (progress payment month fuel price index - month prior to tender closing fuel price index) is positive, the Contractor shall receive a payment.

e) When (I-Bc) (progress payment month fuel price index - month prior to tender closing fuel price index) is negative the Owner shall receive a credit.

f)  	The Contractor shall show the fuel price adjustment as a line item on each progress payment certificate and the final payment certificate. The item shall be called fuel price adjustment.

Fuel Price Adjustment Flow Through Calculation

a) 	The Contractor agrees to adjust the payment to each trucker hired directly by the Contractor for execution of part of the Work according to the following formula:

Tfpa=Tmpp× (I-Bt)Bt ×0.17

Where:

Tfpa = fuel price adjustment paid to trucker, in dollars

Tmpp = monthly payment to trucker, in dollars

Bt = fuel price index in the month that the Contract with the trucker was entered into either verbally or in writing

I = progress payment month fuel price index (for the month that the work was completed in)

The fuel price adjustment paid to each trucker (Tfpa) shall be calculated for each calendar month and may be positive or negative.

b) 	The Contractor agrees to adjust the payment to each Subcontractor according to the following formula:

Sfpa=Smpp× (I-Bs)Bs × Fn100

Where:

Sfpa = fuel price adjustment paid to the Subcontractor, in dollars

Smpp = monthly progress payment to the Subcontractor, in dollars

Bs = fuel price index in the month that the Contract with the Subcontractor was entered into either verbally or in writing

I = progress payment month fuel price index (for the month that the work was completed in)

Fn = fuel consumption factor as negotiated between the Contractor and the Subcontractor as a percentage of the value of the subcontract

c) 	The Contractor shall report the negotiated fuel consumption factor (Fn) on MTO form PH-CC-744, Fuel Consumption Listing Subcontractor, listing all subcontracts, and the corresponding negotiated fuel consumption factor. The form shall be updated monthly or as changes and additions arise.

d) 	The Contractor also agrees that each subcontract shall contain a requirement that the Subcontractor shall make a fuel price adjustment to each trucker hired directly by the Subcontractor for execution of part of the work according to the same formula and conditions used by the Contractor to make fuel price adjustments to truckers, and provide such confirmation on MTO form PH-CC-745, Fuel Consumption Tracking Subcontractor, for each trucker.

Table 8.02.04.02-1

Fuel Consumption Rates

|  | Item Description | Notes | Diesel Fuel Consumption Rates |
| --- | --- | --- | --- |
| 1 | Clearing including Close Cut Clearing |  | 237 l/ha |
| 2 | Grubbing |  | 163 l/ha |
| 3 | Earth Excavation and Earth Borrow | 1 | 1.7 l/m3 |
| 4 | Rock Excavation | 2 | 0.6 l/m3 |
| 5 | Rock Embankment |  | 1.6 l/m³ |
| 6 | Rock Face |  | 1.2 l/m² |
| 7 | Select Subgrade Material (SSM) |  | 1.0 l/t |
| 8 | Granular A, B, O, M, and RSS Backfill | 9 | 1.9 l/t |
| 9 | All Asphalt Pavement, except Superpave FC2 Pavement | 10 | 11.5 l/t |
| 10 | Superpave FC2 Pavement | 10 | 14.3 l/t |
| 11 | Concrete Pavement |  | 4.9 l/m² |
| 12 | Structural Concrete | 3 | 5.5 l/m³ |
| 13 | Tall Wall, any non-precast barrier wall, including asymmetric |  | 3.2 l/m |
| 14 | Milling by m2 Items | 4 | 0.4 l/m² |
| 15 | Milling by tonne Items | 5 | 3.0 l/t |
| 16 | Pulverize |  | 0.2 l/m² |
| 17 | Cold In Place Recycling |  | 0.4 l/m² |
| 18 | Concrete Removal, all complete structural concrete | 6 | 1.0 l/m³ |
| 19 | Concrete Removal, concrete base and pavements |  | 0.9 l/m² |
| 20 | Asphalt Removal | 7 | 0.4 l/m² |
| 21 | Piling |  | 5.0 l/m |
| 22 | Sewers & Drainage | 8 | 8.0 l/m |
| 23 | Rock Supply |  | 1.4 l/m³ |
| 24 | Recycled Asphalt Pavement |  | 0.21 l/m² |
| 25 | Hot-In-Place Recycling (HIR) |  | 0.32 l/m2 |
| 26 | Caisson and Continuous Flight Auger (CFA) Piles (Earth) | 11 | 12.2 l/m3 |
| 27 | Caisson and Continuous Flight Auger (CFA) Piles (Rock) | 11 | 36.6 l/m3 |

Notes: - Also includes the tender item Earth Excavation for Structures when the quantity is greater than 100 m³. - If the Contract has a Rock Excavation item but not the Rock Embankment item, the diesel fuel consumption rate for Rock Excavation shall be 2.2 l/m³. - Structural concrete is normally a lump sum item that has no quantity listed in the Contract Documents. The Contract Administrator will calculate the quantity for this item or get concrete ticket summary sheets for this item. This item does not include deck joint assemblies or modifications, concrete patches, or precast units. Includes the following items: - concrete in deck - high performance concrete in sub structures - concrete in substructure - concrete in structure - concrete in culverts - concrete in approach slab - high performance concrete in deck - high performance concrete in barrier walls - concrete in footing, structure - concrete in parapet walls - concrete in substructure and retaining wall - Includes the following items: - removal of asphalt pavement from concrete surfaces - removal of asphalt pavement, partial depth - removal of asphalt pavement from concrete surfaces on structures - reclaim asphalt pavement, full depth - remove asphalt pavement and salvage; full depth - reclaim asphalt pavement, full depth over concrete - Includes the following items: - reclaim asphalt pavement, partial depth - remove asphalt pavement and salvage, partial depth - Includes the following items: - removal of bridge structures - concrete removal, full depth - concrete removal, complete deck - Includes the following items: - removal of asphalt pavement - Sewers and drainage is to be applied to sewers that are 300 mm in diameter or larger. Subdrains do not receive compensation. Catchbasins with a single stub outlet receive no compensation nor do flexible pipe culverts. - 60% of the Diesel Fuel Consumption Rate shall apply to the production and stockpiling of Granular A,B, O, and RSS Backfill. 40% of the Diesel Fuel Consumption Rate shall apply to Granular A, B, O, and RSS Backfill supplied from existing stockpiles that are the property of the Owner. - When measurement for payment of asphalt is by square metre, for the purpose of fuel price index payment adjustment calculation, square metre asphalt quantities shall be converted to tonnage (Tmix) using the following formula, rounded to one decimal according to LS-100: Tmix = [BRDs x (TD/1000) x Amix] Where: BRDs = 2.50 t/m³ TD = average asphalt thickness from core measurements, mm Amix = quantity of asphalt placed, m² - Fuel consumption rates for Caisson and Continuous Flight Auger (CFA) Piles listed above shall be converted to a l/m rate using the following formula and the diameter of each pile, rounded to one decimal according to LS-100: DFCRl/m = DFCRl/m3 x 0.785 x D2 Where: DFCRl/m3 = Diesel fuel consumption rate in litres per cubic metre for earth or rock caisson or continuous flight auger pile as specified above D = diameter of caisson or continuous flight auger pile, m